## Dashboard
ACTION PLAN TEMPLATE
DASHBOARD
GOALS | Navigation | Number of Goals | Number of Actions | Action Progress
Increase relevant traffic | Go to Goal
Grow your email list | Go to Goal | 5 | 11 | 63.18%
Maintaining the website | Go to Goal
Partner with influencers | Go to Goal
Test 1 | Go to Goal
Terms of Use
20,0%
WATCH PRODUCT VIDEO
DASHBOARD SECTION
You can input your goals into the "GOALS" section.
When you input your goals into this table, you will see the navigation button to go to the related goal sheet.
You can track your goals and actions from the charts and boards.
contact@someka.net
Get Full Version
Unlock tables, remove logo and access many other cool features.
GET FULL VERSION
WITH PASSWORD

## Goal1
ACTION PLAN TEMPLATE
GOAL - 1
GOAL | Increase relevant traffic |  |  |  |  | Achieved
Risks |  |  | Opportunities
There may be an increase in customer service |  |  | Increase in sales
Increase in brand awareness
Action | Responsible Person | Priority | Start Date | Due Date | Progress (%) | Status
Perform keyword research | Kate Burke | High | 2022-03-01 | 2022-06-15 | 100 | Done
Create memorable content | Ann Bailey | Low | 2022-04-20 | 2022-07-01 | 100 | Done
Write guest posts | Mike Oakey | Low | 2021-08-15 | 2021-12-25 | 100 | Done
Formulas:
Status = IFERROR(IF(LEN([Action])=0,"",IF(AND(LEN([Due Date])>0,TODAY()>[Due Date],[Progress (%)]<>100),"Overdue",IF([Progress (%)]=0,"Not Started",IF(AND([Progress (%)]>0,[Progress (%)]<100),"In Progress",IF([Progress (%)]=100,"Done",""))))),"")
Back to
Menu
GOAL SECTION
You should select your goal progress from the dropdown list.
You can add risks and opportunities to your goal.
You can input your actions and properties.
The Start Date is the date that you start the action and, the Due Date is the date set for the end of the action
If today's date is greater than the due date, you will see the "Overdue" in the "Status" section and the "!" sign.
GET FULL VERSION
WITH PASSWORD

## Goal2
ACTION PLAN TEMPLATE
GOAL - 2
GOAL | Grow your email list |  |  |  |  | In Progress
Risks |  |  | Opportunities
Reply to more emails |  |  | Increase in sales
Increase in brand awareness
Action | Responsible Person | Priority | Start Date | Due Date | Progress (%) | Status
Creating coupons for products | Clara Swanson | High | 2022-08-02 | 2022-09-20 |  | Overdue | !
Offer deals | Maya Kos | High | 2022-04-15 | 2022-05-01 | 30 | Overdue | !
Use paid advertising | Thomas Peterson | Low | 2022-04-01 | 2022-07-01 | 100 | Done
Formulas:
Status = IFERROR(IF(LEN([Action])=0,"",IF(AND(LEN([Due Date])>0,TODAY()>[Due Date],[Progress (%)]<>100),"Overdue",IF([Progress (%)]=0,"Not Started",IF(AND([Progress (%)]>0,[Progress (%)]<100),"In Progress",IF([Progress (%)]=100,"Done",""))))),"")
Back to
Menu
GOAL SECTION
You should select your goal progress from the dropdown list.
You can add risks and opportunities to your goal.
You can input your actions and properties.
The Start Date is the date that you start the action and, the Due Date is the date set for the end of the action
If today's date is greater than the due date, you will see the "Overdue" in the "Status" section and the "!" sign.
GET FULL VERSION
WITH PASSWORD

## Goal3
ACTION PLAN TEMPLATE
GOAL - 3
GOAL | Maintaining the website |  |  |  |  | In Progress
Risks |  |  | Opportunities
Customers will not be able to access the site for a while |  |  | There may be an increase in website traffic
Existing problems can be solved
New problems can be found and solved
Action | Responsible Person | Priority | Start Date | Due Date | Progress (%) | Status
Updating website background codes | Ann Bailey | High | 2022-05-01 | 2022-06-30 | 10 | Overdue | !
Interface update | Peter Thomson | Low | 2022-04-10 | 2022-05-30 | 25 | Overdue | !
Formulas:
Status = IFERROR(IF(LEN([Action])=0,"",IF(AND(LEN([Due Date])>0,TODAY()>[Due Date],[Progress (%)]<>100),"Overdue",IF([Progress (%)]=0,"Not Started",IF(AND([Progress (%)]>0,[Progress (%)]<100),"In Progress",IF([Progress (%)]=100,"Done",""))))),"")
Back to
Menu
GOAL SECTION
You should select your goal progress from the dropdown list.
You can add risks and opportunities to your goal.
You can input your actions and properties.
The Start Date is the date that you start the action and, the Due Date is the date set for the end of the action
If today's date is greater than the due date, you will see the "Overdue" in the "Status" section and the "!" sign.
GET FULL VERSION
WITH PASSWORD

## Goal4
ACTION PLAN TEMPLATE
GOAL - 4
GOAL | Partner with influencers |  |  |  |  | In Progress
Risks |  |  | Opportunities
Inauthentic partnerships and content |  |  | Increase in sales
Ethical implications |  |  | Increase in brand awareness
Action | Responsible Person | Priority | Start Date | Due Date | Progress (%) | Status
Influencer research | Oswald Tailor | Low | 2022-05-01 | 2022-05-30 | 70 | Overdue | !
Meeting with agencies | Kate Burke | Low | 2022-04-10 | 2022-04-11 | 100 | Done
Formulas:
Status = IFERROR(IF(LEN([Action])=0,"",IF(AND(LEN([Due Date])>0,TODAY()>[Due Date],[Progress (%)]<>100),"Overdue",IF([Progress (%)]=0,"Not Started",IF(AND([Progress (%)]>0,[Progress (%)]<100),"In Progress",IF([Progress (%)]=100,"Done",""))))),"")
Back to
Menu
GOAL SECTION
You should select your goal progress from the dropdown list.
You can add risks and opportunities to your goal.
You can input your actions and properties.
The Start Date is the date that you start the action and, the Due Date is the date set for the end of the action
If today's date is greater than the due date, you will see the "Overdue" in the "Status" section and the "!" sign.
GET FULL VERSION
WITH PASSWORD

## Goal5
ACTION PLAN TEMPLATE
GOAL - 5
GOAL | Test 1 |  |  |  |  | In Progress
Risks |  |  | Opportunities
sddsfd |  |  | dfdsfdsfsdf
dfdsfdf
Action | Responsible Person | Priority | Start Date | Due Date | Progress (%) | Status
sdasdasd | sdsfdsf | Medium | 2024-04-01 | 2024-05-01 | 60 | In Progress
Formulas:
Status = IFERROR(IF(LEN([Action])=0,"",IF(AND(LEN([Due Date])>0,TODAY()>[Due Date],[Progress (%)]<>100),"Overdue",IF([Progress (%)]=0,"Not Started",IF(AND([Progress (%)]>0,[Progress (%)]<100),"In Progress",IF([Progress (%)]=100,"Done",""))))),"")
Back to
Menu
GOAL SECTION
You should select your goal progress from the dropdown list.
You can add risks and opportunities to your goal.
You can input your actions and properties.
The Start Date is the date that you start the action and, the Due Date is the date set for the end of the action
If today's date is greater than the due date, you will see the "Overdue" in the "Status" section and the "!" sign.
GET FULL VERSION
WITH PASSWORD

## Goal6
ACTION PLAN TEMPLATE
GOAL - 6
GOAL
Risks |  |  | Opportunities
Action | Responsible Person | Priority | Start Date | Due Date | Progress (%) | Status
Formulas:
Status = IFERROR(IF(LEN([Action])=0,"",IF(AND(LEN([Due Date])>0,TODAY()>[Due Date],[Progress (%)]<>100),"Overdue",IF([Progress (%)]=0,"Not Started",IF(AND([Progress (%)]>0,[Progress (%)]<100),"In Progress",IF([Progress (%)]=100,"Done",""))))),"")
Back to
Menu
GOAL SECTION
You should select your goal progress from the dropdown list.
You can add risks and opportunities to your goal.
You can input your actions and properties.
The Start Date is the date that you start the action and, the Due Date is the date set for the end of the action
If today's date is greater than the due date, you will see the "Overdue" in the "Status" section and the "!" sign.
GET FULL VERSION
WITH PASSWORD

## Calc (hidden)
|  |  |  | Priority |  | Progress | Status of Tasks |  |  |  | Percantages
Goals | Status | Statuses | Actions | High | Low | Total | Not Started | In Progress | Done | Overdue | Index | 0% | <=50% | >50% | 100% | Dropdown List
Goal1 | Active | Achieved | 3 | 1 | 0 | 300 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 | 0
Goal2 | Active | In Progress | 3 | 2 | 0 | 130 | 0 | 0 | 1 | 2 | 2 | 0 | 1 | 0 | 1 | 10
Goal3 | Active | In Progress | 2 | 1 | 0 | 35 | 0 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 20
Goal4 | Active | In Progress | 2 | 0 | 0 | 170 | 0 | 0 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 30
Goal5 | Active | In Progress | 1 | 0 | 0 | 60 | 0 | 1 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 40
Goal6 | Passive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 50
60
70
| High | Low | Average Action Progress | Not Started | In Progress | Done | Overdue | [8 empty] | 80
SUM | 4 | 0 | 63.18% | 0 | 1 | 5 | 5 | [8 empty] | 90
100
Action by Progress |  |  | Goals | Actions
0% | 0 |  | 5 | 11
<=50% | 3
>50% | 2
100% | 5
Goals by Status
Achieved | 1
In Progress | 4
On Hold | 0
Cancelled | 0
Goals by Progress
Achieved | 20%
Remaining | 80%

## ToU
TERMS OF USE
END USER LICENSE AGREEMENT
This End-User License Agreement is a legal agreement between you and someka.net that covers all Microsoft Excel templates, spreadsheets or software built by someka.net.
By downloading, copying, accessing or otherwise using any of these templates, you agree to abide by the following terms:
* You may NOT sell, resell, license, rent, lease, lend or otherwise transfer for value without written permission of someka.net * Unless you've purchased the proper license rights, you may NOT remove or alter any someka.net logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within the template. * You may NOT distribute, publish to an online gallery, host on a website, or place on any server in a way that makes it available to the general public.
RESERVATION OF RIGHTS
All title and copyrights in and to the Template, and any copies of the Template, are owned by someka.net. All rights not expressly granted are reserved by someka.net. Use of any Template for any purpose other than expressly permitted in this EULA is prohibited, and may result in severe civil and criminal penalties.
CONTACT
For more information and specific permissions for your case, please contact us at: contact@someka.net
Back to
Menu