## Menu
WBS GANTT CHART EXCEL TEMPLATE
MENU
Terms of Use
contact@someka.net
WBS GANTT CHART TEMPLATE
You need to fill settings first.
You can enter your tasks to task plan list.
You can make analysis of your task in dashboard.
you can see details of Gantt chart in Gantt Chart sheet.
You can see your tasks on calendar in Calendar sheet.
WATCH PRODUCT VIDEO
CALENDAR
GANT CHART
DASHBOARD
TASK PLAN
SETTINGS
GET FULL VERSION
WITH PASSWORD

## Settings
WBS GANTT CHART EXCEL TEMPLATE
SETTINGS
PROJECT SETTINGS |  | CALENDAR SETTINGS |  | EMPLOYEE SETTINGS
Project start date | 2024-04-01 | First day of a week | MONDAY | Employee Name | Department
|  |  |  | Saifur Rohman | Project Manager
Priority List |  | Exclude week days | Yes | Ismail | Business Analyst
| High | Monday |  | Jemmy | Developer
| Medium | Tuesday |  | Rachmat | Quality Assurance
| Low | Wednesday
Thursday
Friday
|  | Saturday | ✓
Type |  | Sunday | ✓
Phase | P
Milestone | M | Exclude holidays | Yes
Task | T | LIST OF HOLIDAYS
Sub-task | S | NAME | DATE
|  | Christmas | 2024-12-24
Status |  | Christmas | 2024-12-25
1 | Done | New Year | 2024-01-01
2 | In Progress | Idul Fitri | 2024-04-10
3 | Not Started | Idul Fitri | 2024-04-11
4
Terms of Use
contact@someka.net
Back to
Menu
HOW TO USE SETTINGS
You can set project start date, priority names, task types and status names.
You can enter your working days special off days in the calendar settings.
You can enter your employees to assign tasks to them.
GET FULL VERSION
WITH PASSWORD

## TaskPlan
WBS GANTT CHART EXCEL TEMPLATE
TASK PLAN
MAIN INFORMATION | [6 empty] | TASK ACTIONS |  |  |  | DETAILS | [6 empty] | Check
ID | Priority | Type | Task | Assign Person | Predecessors' IDs | Planned Duration (Working days) | Delayed start | Elongate | Status | Notes/Actions | Early Start | Early Finish | Late Start | Late Finish | Remain Days | Slack | Real Duration | Error Check
1 | High | M | Start | [5 empty] | Done |  | 2024-04-01 | 2024-04-01 | 2024-04-03 | 2024-04-03 | Done | 2 | 0
2 | Medium | P | Phase 1: Planning | Saifur Rohman |  | 0 |  |  | In progress |  | 2024-04-01 | 2024-04-30 | 2024-04-01 | 2024-04-30 | Done | 0 | 29
3 | High | T | Define project scope and objectives | Saifur Rohman | 1 | 5 |  |  | Done | Schedule and lead meetings with stakeholders to gather requirements | 2024-04-01 | 2024-04-08 | 2024-04-05 | 2024-04-16 | Done | 4 | 5
4 | Low | S | Identify stakeholders and gather requirements | Ismail | 1 | 7 | 2 |  | Done | Identify all stakeholders, conduct interviews, and gather requirements. | 2024-04-03 | 2024-04-16 | 2024-04-03 | 2024-04-16 | Done | 0 | 7
5 | Low | T | Develop project charter and plan | Jemmy | 3,4 | 10 |  |  | Done | Create the project schedule, assign resources, and develop the project plan. | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-04-30 | Done | 0 | 10
6 | Medium | T | Secure funding and resources | Ismail | 4 | 5 |  |  | Done | Present them to stakeholders, and secure funding and resources. | 2024-04-16 | 2024-04-23 | 2024-04-16 | 2024-04-23 | Done | 0 | 5
7 | Low | P | Phase 2: Design | Ismail |  | 20 |  |  |  |  | 2024-04-23 | 2024-05-15 | 2024-04-23 | 2024-05-15 | 45 | 0 | 22
8 | Medium | T | Create detailed design specifications | Ismail | 6 | 15 | 1 |  | Done | Work with the project team to create detailed design specifications for the project. | 2024-04-24 | 2024-05-15 | 2024-04-24 | 2024-05-15 | Done | 0 | 15
9 | Low | S | Review and approve design | Ismail | 6 | 5 |  | 2 | In progress | Prepare design to ensure it meets all requirements and specifications. | 2024-04-23 | 2024-05-02 | 2024-04-23 | 2024-05-02 | 32 | 0 | 7
10 | High | M | Design Approved | Ismail | 9 | 5 |  |  | Not started |  | 2024-05-02 | 2024-05-09 | 2024-05-02 | 2024-05-09 | 39 | 0 | 5
#VALUE!
#VALUE!
Formulas:
DETAILS = IFERROR(IF(ISNUMBER([MAIN INFORMATION]),INDEX(Calculations!Y$7:Y18,MATCH([MAIN INFORMATION],Calculations!$B7:B18,0),1),""),"")
Early Finish = IFERROR(IF(ISNUMBER([MAIN INFORMATION]),INDEX(Calculations!Z$7:Z18,MATCH([MAIN INFORMATION],Calculations!$B7:B18,0),1),""),"")
Late Start = IFERROR(IF(ISNUMBER([MAIN INFORMATION]),INDEX(Calculations!AA$7:AA18,MATCH([MAIN INFORMATION],Calculations!$B7:B18,0),1),""),"")
Late Finish = IFERROR(IF(ISNUMBER([MAIN INFORMATION]),INDEX(Calculations!AB$7:AB18,MATCH([MAIN INFORMATION],Calculations!$B7:B18,0),1),""),"")
Remain Days = IFERROR(IF(Calculations!N7=Status1,Status1,IF([Late Finish]-TODAY()<0,"Overdue!",[Late Finish]-TODAY())),"")
Back to
Menu
HOW TO FILL TASK PLAN
You enter your tasks and assign employees to these task.
You need to input the predecessor ID to each task to see the Gantt Chart properly.
You can update status for each task.
You can also take your notes or assign action the each task.
Once you choose Phase, From Predecessors ID to Status will be grey out. It means these will be calculated automatically.
GET FULL VERSION
WITH PASSWORD
Get Full Version
Unlock tables, remove logo and access many other cool features.

## GanttChart
WBS GANTT CHART EXCEL TEMPLATE
GANTT CHART
|  | SELECTION PANEL | [12 empty] | LEGEND
|  | Priority | Show |  | Phase |  | Show |  |  | Task |  | Show |  |  | Phase | [6 empty] | Task Days | [6 empty] | Sub-task Days | [6 empty] | Slack Days
|  | Status | Show |  | Milestone |  | Show |  |  | Sub-task |  | Show |  |  | Task with 0 day |  |  |  | 1 |  |  | Milestone |  |  |  | 1 |  |  | Off days | [6 empty] | Today
[11 empty] | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 1 | 1
ID | Task Name |  |  |  |  | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
[6 empty] | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05
1 | Start |  |  | 1 | M | 2024-04-01: -1; 2024-04-02: 2
2 | Phase 1: Planning |  |  | 1 | P | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
3 | Define project scope and objectives |  |  | 1 | T | 2024-04-01: 1; 2024-04-02: 1; 2024-04-03: 1; 2024-04-04: 1; 2024-04-05: 1; 2024-04-06: 1; 2024-04-07: 1; 2024-04-08: 2; 2024-04-09: 2; 2024-04-10: 2; 2024-04-11: 2; 2024-04-12: 2; 2024-04-13: 2; 2024-04-14: 2; 2024-04-15: 2
4 | Identify stakeholders and gather requirements |  |  | 1 | S | bar: 2024-04-03 to 2024-04-15
5 | Develop project charter and plan |  |  | 1 | T | bar: 2024-04-16 to 2024-04-29
6 | Secure funding and resources |  |  | 1 | T | bar: 2024-04-16 to 2024-04-22
7 | Phase 2: Design |  |  | 2 | P | 2024-04-23: 3; 2024-04-24: 3; 2024-04-25: 3; 2024-04-26: 3; 2024-04-27: 3; 2024-04-28: 3; 2024-04-29: 3; 2024-04-30: 3; 2024-05-01: 3; 2024-05-02: 3; 2024-05-03: 3; 2024-05-04: 3; 2024-05-05: 3
8 | Create detailed design specifications |  |  | 1 | T | bar: 2024-04-24 to 2024-05-05
9 | Review and approve design |  |  | 2 | S | bar: 2024-04-23 to 2024-05-01
10 | Design Approved |  |  | 3 | M | bar: 2024-05-02 to 2024-05-05
Back to
Menu
HOW TO USE GANTT CHART
You can show or hide task type under selection pane.
You can see Gantt Chart diagram here. Colors and shapes are explained in Legend Section.
GET FULL VERSION
WITH PASSWORD

## Calendar
WBS GANTT CHART EXCEL TEMPLATE
CALENDAR
| YEAR | MONTH | PRIORITY | ASSIGNED | TYPE
| 2024 | April | All | All | All
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07
Start | Start | Start
Phase 1: Planning | Phase 1: Planning | Phase 1: Planning | Phase 1: Planning | Phase 1: Planning
Define project scope and objectives | Define project scope and objectives | Define project scope and objectives | Define project scope and objectives | Define project scope and objectives
|  | Identify stakeholders and gather requirements | Identify stakeholders and gather requirements | Identify stakeholders and gather requirements
2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14
Phase 1: Planning | Phase 1: Planning |  |  | Phase 1: Planning
Define project scope and objectives | Define project scope and objectives |  |  | Define project scope and objectives
Identify stakeholders and gather requirements | Identify stakeholders and gather requirements |  |  | Identify stakeholders and gather requirements
2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21
Phase 1: Planning | Phase 1: Planning | Phase 1: Planning | Phase 1: Planning | Phase 1: Planning
Define project scope and objectives | Define project scope and objectives
Identify stakeholders and gather requirements | Identify stakeholders and gather requirements
| Develop project charter and plan | Develop project charter and plan | Develop project charter and plan | Develop project charter and plan
| Secure funding and resources | Secure funding and resources | Secure funding and resources | Secure funding and resources
2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28
Phase 1: Planning | Phase 1: Planning | Phase 1: Planning | Phase 1: Planning | Phase 1: Planning
Develop project charter and plan | Develop project charter and plan | Develop project charter and plan | Develop project charter and plan | Develop project charter and plan
Secure funding and resources | Secure funding and resources | Create detailed design specifications | Create detailed design specifications | Create detailed design specifications
| Phase 2: Design | Phase 2: Design | Phase 2: Design | Phase 2: Design
| Review and approve design | Review and approve design | Review and approve design | Review and approve design
2024-04-29 | 2024-04-30
Phase 1: Planning | Phase 1: Planning
Develop project charter and plan | Develop project charter and plan
Phase 2: Design | Phase 2: Design
Create detailed design specifications | Create detailed design specifications
Review and approve design | Review and approve design
Formulas:
MONTH = IFERROR(IF(LEN([YEAR])>0,[YEAR]+1,IF(WEEKDAY(Calculations!$GY4,2)=MATCH(I8,Calculations!$CI24:CI30,0),Calculations!$GY4,"")),"")
MONTH = IFERROR(IF(LEN([YEAR])<1,"",IF(MONTH([YEAR]+1)=MONTH([YEAR]),[YEAR]+1,"")),"")
PRIORITY = IFERROR(IF(LEN([MONTH])>0,[MONTH]+1,IF(WEEKDAY(Calculations!$GY4,2)=MATCH(L8,Calculations!$CI24:CI30,0),Calculations!$GY4,"")),"")
PRIORITY = IFERROR(IF(LEN([MONTH])<1,"",IF(MONTH([MONTH]+1)=MONTH([MONTH]),[MONTH]+1,"")),"")
ASSIGNED = IFERROR(IF(LEN([PRIORITY])>0,[PRIORITY]+1,IF(WEEKDAY(Calculations!$GY4,2)=MATCH(O8,Calculations!$CI24:CI30,0),Calculations!$GY4,"")),"")
ASSIGNED = IFERROR(IF(LEN([PRIORITY])<1,"",IF(MONTH([PRIORITY]+1)=MONTH([PRIORITY]),[PRIORITY]+1,"")),"")
TYPE = IFERROR(IF(LEN([ASSIGNED])>0,[ASSIGNED]+1,IF(WEEKDAY(Calculations!$GY4,2)=MATCH(R8,Calculations!$CI24:CI30,0),Calculations!$GY4,"")),"")
TYPE = IFERROR(IF(LEN([ASSIGNED])<1,"",IF(MONTH([ASSIGNED]+1)=MONTH([ASSIGNED]),[ASSIGNED]+1,"")),"")
Back to
Menu
CALENDAR VIEW
You can see your tasks in calendar view here.
You can filter your tasks using above dropdowns.
You can change month and year using filters.
Terms of Use
contact@someka.net
GET FULL VERSION
WITH PASSWORD

## Dashboard
WBS GANTT CHART EXCEL TEMPLATE
DASHBOARD
Person | Department | From Date | To Date | Status | Priority
All | All | All | All | All | All
|  |  |  | Total Planned Days | Total Milestone
|  |  |  | 44 | 2
|  |  |  | Total Days Spent | Total Task
|  |  |  | -1 | 4
|  |  |  | Total Task Completed | Total Subtask
|  |  |  | 7 | 2
Terms of Use
contact@someka.net
Back to
Menu
DASHBOARD
You can analyze your tasks by using filters.
Charts will be updated accordingly.
GET FULL VERSION
WITH PASSWORD

## Calculations (hidden)
[26 empty] | CRITICAL PATH CALCULATION | [17 empty] | REFERENCE | [33 empty] | CALENDAR | [38 empty] | Dynamic Gantt chart | [12 empty] | Dropdowns
10 | 12 | [81 empty] | show | [87 empty] | 2024-04-01
USER DATA | [16 empty] | Error Check | [26 empty] | Precedents - Previous ID | [10 empty] | Dependents - Next ID | [22 empty] | 4 |  |  |  | All filters | 3 | [34 empty] | 20 | [13 empty] | 4 |  |  |  | 5 |  |  | 4 |  |  | 4 | 0 | 5 | [5 empty] | 3 |  |  | 3 | [7 empty] | 3 |  |  | 2
ID | Priority | Type | Desc | Person | Dept | Predecessors' IDs | Planned Duration (Working days) | Delay | Elongate | Real Duration | Next Phase Row | Progress % | Active? | Active-Dashboard |  | Gantt Priority | Priority | Type | Person | Progress | Total | ES date | EF date | LS date | LF date | ES | EF | LS | LF | Slack | Early Finish of Precedents | [9 empty] | Late Start of Successors |  | Critical Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Total | Number of Dependents | Number of Precedents |  |  | Calendar start date |  |  |  |  | List working days | -1 | List of tasks | Month Filter | Priority | Assigned | Type |  | Finish date | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | Final Number | Max 10 events | Active? | Sort | Desc | Type | ES date | EF date | Delay | LF date | Priority | Status | Cond Priority | Cond Status |  | Employee |  | All |  | Dep |  | All |  |  | All |  |  | All | Year | All |  |  |  | All |  | Status | Count | Perc | Priority | Count |  | Employee | Count |  |  |  | Employee | Count | Phase | Name | Status | Done | In Progress | Not Started | Count |  | Event Numbering
1 | High | M | Start |  |  |  | 0 | 0 | 0 | 0 |  | Done | 1 | 1 | 1 - Start | 1 | 0 | 0 |  | 0 | 0 | 2024-04-01 | 2024-04-01 | 2024-04-03 | 2024-04-03 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | No | [11 empty] | 3 | 4 | [8 empty] | 3 | 2 | 0 |  |  | 0 | ✓ | ! |  |  | 2024-04-01 | 0 | 1 - Start | 1 | 1 | 1 | 1 | 1 | 2024-04-03 | [31 empty] | 1 | 1 | 1 | 1 | Start | M | 2024-04-01 | 2024-04-01 | 0 | 2024-04-03 | High | Done | 1 | 1 | 1 | Saifur Rohman | 1 | Saifur Rohman | 1 | Project Manager | 1 | Project Manager | High | 1 | High | Done | 1 | Done | 2024 | Phase | 0 | 2024 | January | 2024-January | 2024-01-01 | Done | 7 | 70% | High | 3 | 1 | Saifur Rohman | 2 | 2 | 2 | 1 | Ismail | 6 |  | Phase 1: Planning | Done | 1 |  |  | 1 | 3 | 1 | bar: 2024-04-01 to 2024-05-01
2 | Medium | P | Phase 1: Planning | Saifur Rohman | Project Manager |  | 0 | 0 | 0 | 29 | 4 | Done | 1 | 1 | 2 - Phase 1: Planning | 2 | 0 | 0 | 0 | 0 | 0 | 2024-04-01 | 2024-04-30 | 2024-04-01 | 2024-04-30 | 0 | 19 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Yes | [22 empty] | 0 | 0 |  |  | 2024-04-01 |  |  |  |  | 2024-04-02 | 1 | 2 - Phase 1: Planning | 1 | 1 | 1 | 1 | 1 | 2024-04-30 | 2 | 2 | 2 | 2 | 2 |  |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  | 2 | 2 | 2 | 2 | Phase 1: Planning | P | 2024-04-01 | 2024-04-30 | 29 | 2024-04-30 | Medium | Done | 2 | 1 | 2 | Ismail | 2 | Ismail | 2 | Business Analyst | 2 | Business Analyst | Medium | 2 | Medium | In Progress | 2 | In Progress | 2024 | Milestone | 0 | 2024 | February | 2024-February | 2024-02-01 | In Progress | 2 | 20% | Medium | 3 | 2 | Ismail | 6 | 1 | 1 | 2 | Saifur Rohman | 2 | 2 | Phase 2: Design | In Progress |  | 1 |  | 1 | 3 | 2
3 | High | T | Define project scope and objectives | Saifur Rohman | Project Manager | 1 | 5 | 0 | 0 | 5 |  | Done | 1 | 1 | 3 - Define project scope and objectives | 1 | 0 | 0 | 0 | 0 | 0 | 2024-04-01 | 2024-04-08 | 2024-04-05 | 2024-04-16 | 0 | 5 | 4 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 |  | No | 1 | [9 empty] | 1 | 5 | [9 empty] | 5 | 1 | 1 | [7 empty] | 2024-04-03 | 2 | 3 - Define project scope and objectives | 1 | 1 | 1 | 1 | 1 | 2024-04-16 | 2024-04-01: 3; 2024-04-02: 3; 2024-04-03: 3; 2024-04-04: 3; 2024-04-05: 3; 2024-04-08: 2; 2024-04-09: 2; 2024-04-12: 2; 2024-04-15: 2; 2024-04-16: 2 | 3 | 3 | 3 | 3 | Define project scope and objectives | T | 2024-04-01 | 2024-04-08 | 5 | 2024-04-16 | High | Done | 1 | 1 | 3 | Jemmy | 3 | Jemmy | 3 | Developer | 3 | Developer | Low | 3 | Low | Not Started | 3 | Not Started |  | Task | 0 | 2024 | March | 2024-March | 2024-03-01 | Not Started | 1 | 10% | Low | 4 | 3 | Jemmy | 1 | 3 | 3 | 3 | Jemmy | 1 | [8 empty] | 3
4 | Low | S | Identify stakeholders and gather requirements | Ismail | Business Analyst | 1 | 7 | 2 | 0 | 7 |  | Done | 1 | 1 | 4 - Identify stakeholders and gather requirements | 3 | 0 | 0 | 0 | 0 | 0 | 2024-04-03 | 2024-04-16 | 2024-04-03 | 2024-04-16 | 2 | 9 | 2 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 |  | Yes | 1 | [9 empty] | 1 | 6 | [9 empty] | 6 | 1 | 1 |  |  | Exclude | Options Chosen |  |  |  | 2024-04-04 | 3 | 4 - Identify stakeholders and gather requirements | 1 | 1 | 1 | 1 | 1 | 2024-04-16 | 2024-04-03: 4; 2024-04-04: 4; 2024-04-05: 4; 2024-04-08: 3; 2024-04-09: 3; 2024-04-12: 3; 2024-04-15: 3; 2024-04-16: 3 | 4 | 4 | 4 | 4 | Identify stakeholders and gather requirements | S | 2024-04-03 | 2024-04-16 | 7 | 2024-04-16 | Low | Done | 3 | 1 | 4 | Rachmat | 4 | Rachmat | 4 | Quality Assurance | 4 | Quality Assurance | [7 empty] | Sub-task | 0 | 2024 | April | 2024-April | 2024-04-01 |  | 0 | 0% |  |  |  | Rachmat | 0 |  |  | 4 | [10 empty] | 4
5 | Low | T | Develop project charter and plan | Jemmy | Developer | 3,4 | 10 | 0 | 0 | 10 |  | Done | 1 | 1 | 5 - Develop project charter and plan | 3 | 0 | 0 | 0 | 0 | 0 | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-04-30 | 9 | 19 | 9 | 19 | 0 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Yes | 3 | 4 | [8 empty] | 3 | [11 empty] | 0 | 2 |  |  | Yes | 1 |  |  |  | 2024-04-05 | 4 | 5 - Develop project charter and plan | 1 | 1 | 1 | 1 | 1 | 2024-04-30 | 2024-04-16: 4; 2024-04-17: 4; 2024-04-18: 4; 2024-04-19: 4; 2024-04-22: 2; 2024-04-23: 2; 2024-04-24: 2; 2024-04-25: 2; 2024-04-26: 2; 2024-04-29: 2; 2024-04-30: 2 | 4 | 5 | 5 | 5 | Develop project charter and plan | T | 2024-04-16 | 2024-04-30 | 10 | 2024-04-30 | Low | Done | 3 | 1 | 5 | [15 empty] | 0 | 2024 | May | 2024-May | 2024-05-01 | Total | 10 | [8 empty] | 5 | [10 empty] | 5
6 | Medium | T | Secure funding and resources | Ismail | Business Analyst | 4 | 5 | 0 | 0 | 5 |  | Done | 1 | 1 | 6 - Secure funding and resources | 2 | 0 | 0 | 0 | 0 | 0 | 2024-04-16 | 2024-04-23 | 2024-04-16 | 2024-04-23 | 9 | 14 | 9 | 14 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14 | Yes | 4 | [9 empty] | 4 | 8 | 9 | [8 empty] | 8 | 2 | 1 |  |  | No | 1 |  |  |  | 2024-04-06 |  | 6 - Secure funding and resources | 1 | 1 | 1 | 1 | 1 | 2024-04-23 | 2024-04-16: 5; 2024-04-17: 5; 2024-04-18: 5; 2024-04-19: 5; 2024-04-22: 3; 2024-04-23: 3 | 5 | 6 | 6 | 6 | Secure funding and resources | T | 2024-04-16 | 2024-04-23 | 5 | 2024-04-23 | Medium | Done | 2 | 1 | 6 | [15 empty] | 0 | 2024 | June | 2024-June | 2024-06-01 | [10 empty] | 6 | [10 empty] | 6
7 | Low | P | Phase 2: Design | Ismail | Business Analyst |  | 0 | 0 | 0 | 22 | 200 | In Progress | 1 | 1 | 7 - Phase 2: Design | 3 | 0 | 0 | 0 | 0 | 0 | 2024-04-23 | 2024-05-15 | 2024-04-23 | 2024-05-15 | 14 | 30 | 14 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Yes | [22 empty] | 0 | 0 | [7 empty] | 2024-04-07 |  | 7 - Phase 2: Design | 1 | 1 | 1 | 1 | 1 | 2024-05-15 | 2024-04-23: 4; 2024-04-24: 4; 2024-04-25: 4; 2024-04-26: 4; 2024-04-29: 3; 2024-04-30: 3; 2024-05-01: 3 | 4 | 7 | 7 | 7 | Phase 2: Design | P | 2024-04-23 | 2024-05-15 | 22 | 2024-05-15 | Low | In Progress | 3 | 2 | 7 | [15 empty] | 0 | 2024 | July | 2024-July | 2024-07-01 | [10 empty] | 7 |  |  | 7
8 | Medium | T | Create detailed design specifications | Ismail | Business Analyst | 6 | 15 | 1 | 0 | 15 |  | Done | 1 | 1 | 8 - Create detailed design specifications | 2 | 0 | 0 | 0 | 0 | 0 | 2024-04-24 | 2024-05-15 | 2024-04-24 | 2024-05-15 | 15 | 30 | 15 | 30 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Yes | 6 | [9 empty] | 6 | [11 empty] | 0 | 1 |  |  | Weekend option | 0000011 |  |  |  | 2024-04-08 | 5 | 8 - Create detailed design specifications | 1 | 1 | 1 | 1 | 1 | 2024-05-15 | 2024-04-24: 3; 2024-04-25: 3; 2024-04-26: 3; 2024-04-29: 4; 2024-04-30: 4; 2024-05-01: 4 | 4 | 8 | 8 | 8 | Create detailed design specifications | T | 2024-04-24 | 2024-05-15 | 15 | 2024-05-15 | Medium | Done | 2 | 1 | 8 | [15 empty] | 0 | 2024 | August | 2024-August | 2024-08-01 | Total Day Spent |  | Number Of Milestone | 3 | [6 empty] | 8
9 | Low | S | Review and approve design | Ismail | Business Analyst | 6 | 7 | 0 | 2 | 7 |  | In progress | 1 | 1 | 9 - Review and approve design | 3 | 0 | 0 | 0 | 0 | 0 | 2024-04-23 | 2024-05-02 | 2024-04-23 | 2024-05-02 | 14 | 21 | 14 | 21 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 |  | Yes | 6 | [9 empty] | 6 | 10 | [9 empty] | 10 | 1 | 1 |  |  | Monday | 0 |  |  |  | 2024-04-09 | 6 | 9 - Review and approve design | 1 | 1 | 1 | 1 | 1 | 2024-05-02 | 2024-04-23: 5; 2024-04-24: 5; 2024-04-25: 5; 2024-04-26: 5; 2024-04-29: 5; 2024-04-30: 5; 2024-05-01: 5 | 5 | 9 | 9 | 9 | Review and approve design | S | 2024-04-23 | 2024-05-02 | 7 | 2024-05-02 | Low | In progress | 3 | 2 | 9 | [15 empty] | 0 | 2024 | September | 2024-September | 2024-09-01 | 44 |  | 2 | Priority | Count | [5 empty] | 9 | [10 empty] | 1
10 | High | M | Design Approved | Ismail | Business Analyst | 9 | 5 | 0 | 0 | 5 |  | Not started | 1 | 1 | 10 - Design Approved | 1 | 0 | 0 | 0 | 0 | 0 | 2024-05-02 | 2024-05-09 | 2024-05-02 | 2024-05-09 | 21 | 26 | 21 | 26 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Yes | 9 | [9 empty] | 9 | [11 empty] | 0 | 1 |  |  | Tuesday | 0 |  |  |  | 2024-04-10 |  | 10 - Design Approved | 0 | 1 | 1 | 1 | 0 | 2024-05-09 | [31 empty] | 0 | 10 | 10 | 10 | Design Approved | M | 2024-05-02 | 2024-05-09 | 5 | 2024-05-09 | High | Not started | 1 | 3 | 10 | [15 empty] | 0 | 2024 | Otcober | 2024-Otcober | 2024-10-01 |  |  |  | High | 3 | [5 empty] | 10 | [10 empty] | 2
- | - | - | - | - | - | - | - | - | - | - |  | - | 1 | 0 | - - - | [5 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Wednesday | 0 |  |  |  | 2024-04-11 |  |  | 0 | 1 | 1 | 1 | 0 | [32 empty] | 0 |  | - | [11 empty] | 11 | [15 empty] | 0 | 2024 | November | 2024-November | 2024-11-01 | Total Day Spent |  | Number Of Task | Medium | 3 | [16 empty] | 3
- | - | - | - | - | - | - | - | - | - | - |  | - | 1 | 0 | - - - | [5 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Thursday | 0 |  |  |  | 2024-04-12 | 7 |  | 0 | 1 | 1 | 1 | 0 | [32 empty] | 0 |  | - | [11 empty] | 12 | [15 empty] | 0 | 2024 | December | 2024-December | 2024-12-01 | -1 |  | 4 | Low | 4 | [16 empty] | 4
- | - | - | [7 empty] | 0 | [6 empty] | 1 | 1 |  |  | 2 | [43 empty] | 4 |  |  |  |  | Friday | 0 |  |  |  | 2024-04-13 | [53 empty] | 13 | [15 empty] | 1 |  | January | [23 empty] | 5
[70 empty] | Saturday | 1 |  |  |  | 2024-04-14 | [53 empty] | 14 | [15 empty] | 1 |  | February |  |  | Total Task Completed |  | Number of Subtasks | [18 empty] | 6
[70 empty] | Sunday | 1 |  |  |  | 2024-04-15 | 8 | [52 empty] | 15 | [15 empty] | 1 |  | March |  |  | 7 |  | 2
[75 empty] | 2024-04-16 | 9 | [52 empty] | 16 | [15 empty] | 1 |  | April
[54 empty] | 4 | [15 empty] | Months | WEEKDAYS |  | 0 |  | 2024-04-17 | 10 | [52 empty] | 17 | [15 empty] | 1 |  | May | [23 empty] | 1
[65 empty] | 9 |  |  |  |  | January | MONDAY | 1 | 1 | Mo | 2024-04-18 | 11 | [52 empty] | 18 | [15 empty] | 1 |  | June | [23 empty] | 2
[70 empty] | February | TUESDAY | 2 | 2 | Tu | 2024-04-19 | 12 | [52 empty] | 19 | [15 empty] | 1 |  | July | [23 empty] | 3
[70 empty] | March | WEDNESDAY | 3 | 3 | We | 2024-04-20 | [69 empty] | 1 |  | August | [23 empty] | 4
[70 empty] | April | THURSDAY | 4 | 4 | Th | 2024-04-21 | [69 empty] | 1 |  | September | [23 empty] | 5
[70 empty] | May | FRIDAY | 5 | 5 | Fr | 2024-04-22 | 13 | [68 empty] | 1 |  | Otcober | [23 empty] | 6
[65 empty] | - |  |  |  |  | June | SATURDAY | 6 | 6 | Sa | 2024-04-23 | 14 | [68 empty] | 1 |  | November
[65 empty] | - |  |  |  |  | July | SUNDAY | 7 | 7 | Su | 2024-04-24 | 15 | [68 empty] | 1 |  | December
[70 empty] | August |  |  |  |  | 2024-04-25 | 16 | [68 empty] | 2 |  | January | [23 empty] | 1
[70 empty] | September |  |  |  |  | 2024-04-26 | 17 | [68 empty] | 2 |  | February | [23 empty] | 2
[70 empty] | Otcober |  |  |  |  | 2024-04-27 | [69 empty] | 2 |  | March | [23 empty] | 3
[70 empty] | November |  |  |  |  | 2024-04-28 | [69 empty] | 2 |  | April | [23 empty] | 4
[70 empty] | December |  |  |  |  | 2024-04-29 | 18 | [68 empty] | 2 |  | May | [23 empty] | 5
[75 empty] | 2024-04-30 | 19 | [68 empty] | 2 |  | June | [23 empty] | 6
[75 empty] | 2024-05-01 | 20 | [68 empty] | 2 |  | July
[69 empty] | 0 | Prorities | All |  |  |  | 2024-05-02 | 21 | [68 empty] | 2 |  | August
[68 empty] | 1 | 1 | High | High |  |  |  | 2024-05-03 | 22 | [68 empty] | 2 |  | September | [23 empty] | 1
[68 empty] | 2 | 2 | Medium | Medium |  |  |  | 2024-05-04 | [69 empty] | 2 |  | Otcober | [23 empty] | 2
[65 empty] | - |  |  | 3 | 3 | Low | Low |  |  |  | 2024-05-05 | [69 empty] | 2 |  | November | [23 empty] | 3
[65 empty] | - |  |  | 4 | [6 empty] | 2024-05-06 | 23 | [68 empty] | 2 |  | December | [23 empty] | 4
[68 empty] | 5 | [6 empty] | 2024-05-07 | 24 | [68 empty] | 3 |  | January | [23 empty] | 5
[75 empty] | 2024-05-08 | 25 | [68 empty] | 3 |  | February | [23 empty] | 6
[68 empty] | 0 | Type | All | Condition | Hide? |  | dropdown | 2024-05-09 | 26 | [68 empty] | 3 |  | March
[68 empty] | 1 | P | Phase | 3 | 1 |  | P | 2024-05-10 | 27 | [68 empty] | 3 |  | April
[68 empty] | 2 | M | Milestone | -1 | 1 |  | M | 2024-05-11 | [69 empty] | 3 |  | May | [23 empty] | 1
[68 empty] | 3 | T | Task | -2 | 1 |  | T | 2024-05-12 | [69 empty] | 3 |  | June | [23 empty] | 2
[68 empty] | 4 | S | Sub-task | -2 | 1 |  | S | 2024-05-13 | 28 | [68 empty] | 3 |  | July | [23 empty] | 3
[75 empty] | 2024-05-14 | 29 | [68 empty] | 3 |  | August | [23 empty] | 4
[68 empty] | 0 | Status | [5 empty] | 2024-05-15 | 30 | [68 empty] | 3 |  | September | [23 empty] | 5
[68 empty] | 1 | 1 | Done | Done |  |  |  | 2024-05-16 | 31 | [68 empty] | 3 |  | Otcober | [23 empty] | 6
[65 empty] | - |  |  | 2 | 2 | In Progress | In Progress |  |  |  | 2024-05-17 | 32 | [68 empty] | 3 |  | November
[65 empty] | - |  |  | 3 | 3 | Not Started | Not Started |  |  |  | 2024-05-18 | [69 empty] | 3 |  | December
[75 empty] | 2024-05-19 | [69 empty] | 4 |  | January
[75 empty] | 2024-05-20 | 33 | [68 empty] | 4 |  | February
[75 empty] | 2024-05-21 | 34 | [68 empty] | 4 |  | March
[75 empty] | 2024-05-22 | 35 | [68 empty] | 4 |  | April
[75 empty] | 2024-05-23 | 36 | [68 empty] | 4 |  | May
[75 empty] | 2024-05-24 | 37 | [68 empty] | 4 |  | June
[75 empty] | 2024-05-25 | [69 empty] | 4 |  | July
[75 empty] | 2024-05-26 | [69 empty] | 4 |  | August
[75 empty] | 2024-05-27 | 38 | [68 empty] | 4 |  | September
[75 empty] | 2024-05-28 | 39 | [68 empty] | 4 |  | Otcober
[65 empty] | - | [9 empty] | 2024-05-29 | 40 | [68 empty] | 4 |  | November
[65 empty] | - | [9 empty] | 2024-05-30 | 41 | [68 empty] | 4 |  | December
[75 empty] | 2024-05-31 | 42 | [68 empty] | 5 |  | January
[75 empty] | 2024-06-01 | [69 empty] | 5 |  | February
[75 empty] | 2024-06-02 | [69 empty] | 5 |  | March
[75 empty] | 2024-06-03 | 43 | [68 empty] | 5 |  | April
[75 empty] | 2024-06-04 | 44 | [68 empty] | 5 |  | May
[75 empty] | 2024-06-05 | 45 | [68 empty] | 5 |  | June
[75 empty] | 2024-06-06 | 46 | [68 empty] | 5 |  | July
[75 empty] | 2024-06-07 | 47 | [68 empty] | 5 |  | August
[75 empty] | 2024-06-08 | [69 empty] | 5 |  | September
[75 empty] | 2024-06-09 | [69 empty] | 5 |  | Otcober
[65 empty] | - | [9 empty] | 2024-06-10 | 48 | [68 empty] | 5 |  | November
[65 empty] | - | [9 empty] | 2024-06-11 | 49 | [68 empty] | 5 |  | December
[75 empty] | 2024-06-12 | 50 | [68 empty] | 6 |  | January
[75 empty] | 2024-06-13 | 51 | [68 empty] | 6 |  | February
[75 empty] | 2024-06-14 | 52 | [68 empty] | 6 |  | March
[75 empty] | 2024-06-15 | [69 empty] | 6 |  | April
[75 empty] | 2024-06-16 | [69 empty] | 6 |  | May
[75 empty] | 2024-06-17 | 53 | [68 empty] | 6 |  | June
[75 empty] | 2024-06-18 | 54 | [68 empty] | 6 |  | July
[75 empty] | 2024-06-19 | 55 | [68 empty] | 6 |  | August
[75 empty] | 2024-06-20 | 56 | [68 empty] | 6 |  | September
[75 empty] | 2024-06-21 | 57 | [68 empty] | 6 |  | Otcober
[65 empty] | - | [9 empty] | 2024-06-22 | [69 empty] | 6 |  | November
[65 empty] | - | [9 empty] | 2024-06-23 | [69 empty] | 6 |  | December
[75 empty] | 2024-06-24 | 58 | [68 empty] | 7 |  | January
[75 empty] | 2024-06-25 | 59 | [68 empty] | 7 |  | February
[75 empty] | 2024-06-26 | 60 | [68 empty] | 7 |  | March
[75 empty] | 2024-06-27 | 61 | [68 empty] | 7 |  | April
[75 empty] | 2024-06-28 | 62 | [68 empty] | 7 |  | May
[75 empty] | 2024-06-29 | [69 empty] | 7 |  | June
[75 empty] | 2024-06-30 | [69 empty] | 7 |  | July
[75 empty] | 2024-07-01 | 63 | [68 empty] | 7 |  | August
[75 empty] | 2024-07-02 | 64 | [68 empty] | 7 |  | September
[75 empty] | 2024-07-03 | 65 | [68 empty] | 7 |  | Otcober
[65 empty] | - | [9 empty] | 2024-07-04 | 66 | [68 empty] | 7 |  | November
[65 empty] | - | [9 empty] | 2024-07-05 | 67 | [68 empty] | 7 |  | December
[75 empty] | 2024-07-06 | [69 empty] | 8 |  | January
[75 empty] | 2024-07-07 | [69 empty] | 8 |  | February
[75 empty] | 2024-07-08 | 68 | [68 empty] | 8 |  | March
[75 empty] | 2024-07-09 | 69 | [68 empty] | 8 |  | April
[75 empty] | 2024-07-10 | 70 | [68 empty] | 8 |  | May
[75 empty] | 2024-07-11 | 71 | [68 empty] | 8 |  | June
[75 empty] | 2024-07-12 | 72 | [68 empty] | 8 |  | July
[75 empty] | 2024-07-13 | [69 empty] | 8 |  | August
[75 empty] | 2024-07-14 | [69 empty] | 8 |  | September
[75 empty] | 2024-07-15 | 73 | [68 empty] | 8 |  | Otcober
[65 empty] | - | [9 empty] | 2024-07-16 | 74 | [68 empty] | 8 |  | November
[65 empty] | - | [9 empty] | 2024-07-17 | 75 | [68 empty] | 8 |  | December
[75 empty] | 2024-07-18 | 76 | [68 empty] | 9 |  | January
[75 empty] | 2024-07-19 | 77 | [68 empty] | 9 |  | February
[75 empty] | 2024-07-20 | [69 empty] | 9 |  | March
[75 empty] | 2024-07-21 | [69 empty] | 9 |  | April
[75 empty] | 2024-07-22 | 78 | [68 empty] | 9 |  | May
[75 empty] | 2024-07-23 | 79 | [68 empty] | 9 |  | June
[75 empty] | 2024-07-24 | 80 | [68 empty] | 9 |  | July
[75 empty] | 2024-07-25 | 81 | [68 empty] | 9 |  | August
[75 empty] | 2024-07-26 | 82 | [68 empty] | 9 |  | September
[75 empty] | 2024-07-27 | [69 empty] | 9 |  | Otcober
[65 empty] | - | [9 empty] | 2024-07-28 | [69 empty] | 9 |  | November
[65 empty] | - | [9 empty] | 2024-07-29 | 83 | [68 empty] | 9 |  | December
[75 empty] | 2024-07-30 | 84
[75 empty] | 2024-07-31 | 85
[75 empty] | 2024-08-01 | 86
[75 empty] | 2024-08-02 | 87
2024-08-03
2024-08-04
[75 empty] | 2024-08-05 | 88
[75 empty] | 2024-08-06 | 89
[75 empty] | 2024-08-07 | 90
[75 empty] | 2024-08-08 | 91
[75 empty] | 2024-08-09 | 92
2024-08-10
2024-08-11
[75 empty] | 2024-08-12 | 93
[75 empty] | 2024-08-13 | 94
[75 empty] | 2024-08-14 | 95
[75 empty] | 2024-08-15 | 96
[75 empty] | 2024-08-16 | 97
2024-08-17
2024-08-18
[75 empty] | 2024-08-19 | 98
[75 empty] | 2024-08-20 | 99
[75 empty] | 2024-08-21 | 100
[75 empty] | 2024-08-22 | 101
[75 empty] | 2024-08-23 | 102
2024-08-24
2024-08-25
[75 empty] | 2024-08-26 | 103
[75 empty] | 2024-08-27 | 104
[75 empty] | 2024-08-28 | 105
[75 empty] | 2024-08-29 | 106
[75 empty] | 2024-08-30 | 107
2024-08-31
2024-09-01
[75 empty] | 2024-09-02 | 108
[75 empty] | 2024-09-03 | 109
[75 empty] | 2024-09-04 | 110
[75 empty] | 2024-09-05 | 111
[75 empty] | 2024-09-06 | 112
2024-09-07
2024-09-08
[75 empty] | 2024-09-09 | 113
[75 empty] | 2024-09-10 | 114
[75 empty] | 2024-09-11 | 115
[75 empty] | 2024-09-12 | 116
[75 empty] | 2024-09-13 | 117
2024-09-14
2024-09-15
[75 empty] | 2024-09-16 | 118
[75 empty] | 2024-09-17 | 119
[75 empty] | 2024-09-18 | 120
[75 empty] | 2024-09-19 | 121
[75 empty] | 2024-09-20 | 122
2024-09-21
2024-09-22
[75 empty] | 2024-09-23 | 123
[75 empty] | 2024-09-24 | 124
[75 empty] | 2024-09-25 | 125
[75 empty] | 2024-09-26 | 126
[75 empty] | 2024-09-27 | 127
2024-09-28
2024-09-29
[75 empty] | 2024-09-30 | 128
[75 empty] | 2024-10-01 | 129
[75 empty] | 2024-10-02 | 130
[75 empty] | 2024-10-03 | 131
[75 empty] | 2024-10-04 | 132
2024-10-05
2024-10-06
[75 empty] | 2024-10-07 | 133
[75 empty] | 2024-10-08 | 134
[75 empty] | 2024-10-09 | 135
[75 empty] | 2024-10-10 | 136
[75 empty] | 2024-10-11 | 137
2024-10-12
2024-10-13
[75 empty] | 2024-10-14 | 138
[75 empty] | 2024-10-15 | 139
[75 empty] | 2024-10-16 | 140
[75 empty] | 2024-10-17 | 141
[75 empty] | 2024-10-18 | 142
2024-10-19
2024-10-20
[75 empty] | 2024-10-21 | 143
[75 empty] | 2024-10-22 | 144
[75 empty] | 2024-10-23 | 145
[75 empty] | 2024-10-24 | 146
[75 empty] | 2024-10-25 | 147
2024-10-26
2024-10-27
[75 empty] | 2024-10-28 | 148
[75 empty] | 2024-10-29 | 149
[75 empty] | 2024-10-30 | 150
[75 empty] | 2024-10-31 | 151
[75 empty] | 2024-11-01 | 152
2024-11-02
2024-11-03
[75 empty] | 2024-11-04 | 153
[75 empty] | 2024-11-05 | 154
[75 empty] | 2024-11-06 | 155
[75 empty] | 2024-11-07 | 156
[75 empty] | 2024-11-08 | 157
2024-11-09
2024-11-10
[75 empty] | 2024-11-11 | 158
[75 empty] | 2024-11-12 | 159
[75 empty] | 2024-11-13 | 160
[75 empty] | 2024-11-14 | 161
[75 empty] | 2024-11-15 | 162
2024-11-16
2024-11-17
[75 empty] | 2024-11-18 | 163
[75 empty] | 2024-11-19 | 164
[75 empty] | 2024-11-20 | 165
[75 empty] | 2024-11-21 | 166
[75 empty] | 2024-11-22 | 167
2024-11-23
2024-11-24
[75 empty] | 2024-11-25 | 168
[75 empty] | 2024-11-26 | 169
[75 empty] | 2024-11-27 | 170
[75 empty] | 2024-11-28 | 171
[75 empty] | 2024-11-29 | 172
2024-11-30
2024-12-01
[75 empty] | 2024-12-02 | 173
[75 empty] | 2024-12-03 | 174
[75 empty] | 2024-12-04 | 175
[75 empty] | 2024-12-05 | 176
[75 empty] | 2024-12-06 | 177
2024-12-07
2024-12-08
[75 empty] | 2024-12-09 | 178
[75 empty] | 2024-12-10 | 179
[75 empty] | 2024-12-11 | 180
[75 empty] | 2024-12-12 | 181
[75 empty] | 2024-12-13 | 182
2024-12-14
2024-12-15
[75 empty] | 2024-12-16 | 183
[75 empty] | 2024-12-17 | 184
[75 empty] | 2024-12-18 | 185
[75 empty] | 2024-12-19 | 186
[75 empty] | 2024-12-20 | 187
2024-12-21
2024-12-22
[75 empty] | 2024-12-23 | 188
2024-12-24
2024-12-25
[75 empty] | 2024-12-26 | 189
[75 empty] | 2024-12-27 | 190
2024-12-28
2024-12-29
[75 empty] | 2024-12-30 | 191
[75 empty] | 2024-12-31 | 192
[75 empty] | 2025-01-01 | 193
[75 empty] | 2025-01-02 | 194
[75 empty] | 2025-01-03 | 195
2025-01-04
2025-01-05
[75 empty] | 2025-01-06 | 196
[75 empty] | 2025-01-07 | 197
[75 empty] | 2025-01-08 | 198
[75 empty] | 2025-01-09 | 199
[75 empty] | 2025-01-10 | 200
2025-01-11
2025-01-12
[75 empty] | 2025-01-13 | 201
[75 empty] | 2025-01-14 | 202
[75 empty] | 2025-01-15 | 203
[75 empty] | 2025-01-16 | 204
[75 empty] | 2025-01-17 | 205
2025-01-18
2025-01-19
[75 empty] | 2025-01-20 | 206
[75 empty] | 2025-01-21 | 207
[75 empty] | 2025-01-22 | 208
[75 empty] | 2025-01-23 | 209
[75 empty] | 2025-01-24 | 210
2025-01-25
2025-01-26
[75 empty] | 2025-01-27 | 211
[75 empty] | 2025-01-28 | 212
[75 empty] | 2025-01-29 | 213
[75 empty] | 2025-01-30 | 214
[75 empty] | 2025-01-31 | 215
2025-02-01
2025-02-02
[75 empty] | 2025-02-03 | 216
[75 empty] | 2025-02-04 | 217
[75 empty] | 2025-02-05 | 218
[75 empty] | 2025-02-06 | 219
[75 empty] | 2025-02-07 | 220
2025-02-08
2025-02-09
[75 empty] | 2025-02-10 | 221
[75 empty] | 2025-02-11 | 222
[75 empty] | 2025-02-12 | 223
[75 empty] | 2025-02-13 | 224
[75 empty] | 2025-02-14 | 225
2025-02-15
2025-02-16
[75 empty] | 2025-02-17 | 226
[75 empty] | 2025-02-18 | 227
[75 empty] | 2025-02-19 | 228
[75 empty] | 2025-02-20 | 229
[75 empty] | 2025-02-21 | 230
2025-02-22
2025-02-23
[75 empty] | 2025-02-24 | 231
[75 empty] | 2025-02-25 | 232
[75 empty] | 2025-02-26 | 233
[75 empty] | 2025-02-27 | 234
[75 empty] | 2025-02-28 | 235
2025-03-01
2025-03-02
[75 empty] | 2025-03-03 | 236
[75 empty] | 2025-03-04 | 237
[75 empty] | 2025-03-05 | 238
[75 empty] | 2025-03-06 | 239
[75 empty] | 2025-03-07 | 240
2025-03-08
2025-03-09
[75 empty] | 2025-03-10 | 241
[75 empty] | 2025-03-11 | 242
[75 empty] | 2025-03-12 | 243
[75 empty] | 2025-03-13 | 244
[75 empty] | 2025-03-14 | 245
2025-03-15
2025-03-16
[75 empty] | 2025-03-17 | 246
[75 empty] | 2025-03-18 | 247
[75 empty] | 2025-03-19 | 248
[75 empty] | 2025-03-20 | 249
[75 empty] | 2025-03-21 | 250
2025-03-22
2025-03-23
[75 empty] | 2025-03-24 | 251
[75 empty] | 2025-03-25 | 252
[75 empty] | 2025-03-26 | 253
[75 empty] | 2025-03-27 | 254
[75 empty] | 2025-03-28 | 255
2025-03-29
2025-03-30
[75 empty] | 2025-03-31 | 256
[75 empty] | 2025-04-01 | 257
[75 empty] | 2025-04-02 | 258
[75 empty] | 2025-04-03 | 259
[75 empty] | 2025-04-04 | 260
2025-04-05
2025-04-06
[75 empty] | 2025-04-07 | 261
[75 empty] | 2025-04-08 | 262
[75 empty] | 2025-04-09 | 263
[75 empty] | 2025-04-10 | 264
[75 empty] | 2025-04-11 | 265
2025-04-12
2025-04-13
[75 empty] | 2025-04-14 | 266
[75 empty] | 2025-04-15 | 267
[75 empty] | 2025-04-16 | 268
[75 empty] | 2025-04-17 | 269
[75 empty] | 2025-04-18 | 270
2025-04-19
2025-04-20
[75 empty] | 2025-04-21 | 271
[75 empty] | 2025-04-22 | 272
[75 empty] | 2025-04-23 | 273
[75 empty] | 2025-04-24 | 274
[75 empty] | 2025-04-25 | 275
2025-04-26
2025-04-27
[75 empty] | 2025-04-28 | 276
[75 empty] | 2025-04-29 | 277
[75 empty] | 2025-04-30 | 278
[75 empty] | 2025-05-01 | 279
[75 empty] | 2025-05-02 | 280
2025-05-03
2025-05-04
[75 empty] | 2025-05-05 | 281
[75 empty] | 2025-05-06 | 282
[75 empty] | 2025-05-07 | 283
[75 empty] | 2025-05-08 | 284
[75 empty] | 2025-05-09 | 285
2025-05-10
2025-05-11
[75 empty] | 2025-05-12 | 286
[75 empty] | 2025-05-13 | 287
[75 empty] | 2025-05-14 | 288
[75 empty] | 2025-05-15 | 289
[75 empty] | 2025-05-16 | 290
2025-05-17
2025-05-18
[75 empty] | 2025-05-19 | 291
[75 empty] | 2025-05-20 | 292
[75 empty] | 2025-05-21 | 293
[75 empty] | 2025-05-22 | 294
[75 empty] | 2025-05-23 | 295
2025-05-24
2025-05-25
[75 empty] | 2025-05-26 | 296
[75 empty] | 2025-05-27 | 297
[75 empty] | 2025-05-28 | 298
[75 empty] | 2025-05-29 | 299
[75 empty] | 2025-05-30 | 300
2025-05-31
2025-06-01
[75 empty] | 2025-06-02 | 301
[75 empty] | 2025-06-03 | 302
[75 empty] | 2025-06-04 | 303
[75 empty] | 2025-06-05 | 304
[75 empty] | 2025-06-06 | 305
2025-06-07
2025-06-08
[75 empty] | 2025-06-09 | 306
[75 empty] | 2025-06-10 | 307
[75 empty] | 2025-06-11 | 308
[75 empty] | 2025-06-12 | 309
[75 empty] | 2025-06-13 | 310
2025-06-14
2025-06-15
[75 empty] | 2025-06-16 | 311
[75 empty] | 2025-06-17 | 312
[75 empty] | 2025-06-18 | 313
[75 empty] | 2025-06-19 | 314
[75 empty] | 2025-06-20 | 315
2025-06-21
2025-06-22
[75 empty] | 2025-06-23 | 316
[75 empty] | 2025-06-24 | 317
[75 empty] | 2025-06-25 | 318
[75 empty] | 2025-06-26 | 319
[75 empty] | 2025-06-27 | 320
2025-06-28
2025-06-29
[75 empty] | 2025-06-30 | 321
[75 empty] | 2025-07-01 | 322
[75 empty] | 2025-07-02 | 323
[75 empty] | 2025-07-03 | 324
[75 empty] | 2025-07-04 | 325
2025-07-05
2025-07-06
[75 empty] | 2025-07-07 | 326
[75 empty] | 2025-07-08 | 327
[75 empty] | 2025-07-09 | 328
[75 empty] | 2025-07-10 | 329
[75 empty] | 2025-07-11 | 330
2025-07-12
2025-07-13
[75 empty] | 2025-07-14 | 331
[75 empty] | 2025-07-15 | 332
[75 empty] | 2025-07-16 | 333
[75 empty] | 2025-07-17 | 334
[75 empty] | 2025-07-18 | 335
2025-07-19
2025-07-20
[75 empty] | 2025-07-21 | 336
[75 empty] | 2025-07-22 | 337
[75 empty] | 2025-07-23 | 338
[75 empty] | 2025-07-24 | 339
[75 empty] | 2025-07-25 | 340
2025-07-26
2025-07-27
[75 empty] | 2025-07-28 | 341
[75 empty] | 2025-07-29 | 342
[75 empty] | 2025-07-30 | 343
[75 empty] | 2025-07-31 | 344
[75 empty] | 2025-08-01 | 345
2025-08-02
2025-08-03
[75 empty] | 2025-08-04 | 346
[75 empty] | 2025-08-05 | 347
[75 empty] | 2025-08-06 | 348
[75 empty] | 2025-08-07 | 349
[75 empty] | 2025-08-08 | 350
2025-08-09
2025-08-10
[75 empty] | 2025-08-11 | 351
[75 empty] | 2025-08-12 | 352
[75 empty] | 2025-08-13 | 353
[75 empty] | 2025-08-14 | 354
[75 empty] | 2025-08-15 | 355
2025-08-16
2025-08-17
[75 empty] | 2025-08-18 | 356
[75 empty] | 2025-08-19 | 357
[75 empty] | 2025-08-20 | 358
[75 empty] | 2025-08-21 | 359
[75 empty] | 2025-08-22 | 360
2025-08-23
2025-08-24
[75 empty] | 2025-08-25 | 361
[75 empty] | 2025-08-26 | 362
[75 empty] | 2025-08-27 | 363
[75 empty] | 2025-08-28 | 364
[75 empty] | 2025-08-29 | 365
2025-08-30
2025-08-31
[75 empty] | 2025-09-01 | 366
[75 empty] | 2025-09-02 | 367
[75 empty] | 2025-09-03 | 368
[75 empty] | 2025-09-04 | 369
[75 empty] | 2025-09-05 | 370
2025-09-06
2025-09-07
[75 empty] | 2025-09-08 | 371
[75 empty] | 2025-09-09 | 372
[75 empty] | 2025-09-10 | 373
[75 empty] | 2025-09-11 | 374
[75 empty] | 2025-09-12 | 375
2025-09-13
2025-09-14
[75 empty] | 2025-09-15 | 376
[75 empty] | 2025-09-16 | 377
[75 empty] | 2025-09-17 | 378
[75 empty] | 2025-09-18 | 379
[75 empty] | 2025-09-19 | 380
2025-09-20
2025-09-21
[75 empty] | 2025-09-22 | 381
[75 empty] | 2025-09-23 | 382
[75 empty] | 2025-09-24 | 383
[75 empty] | 2025-09-25 | 384
[75 empty] | 2025-09-26 | 385
2025-09-27
2025-09-28
[75 empty] | 2025-09-29 | 386
[75 empty] | 2025-09-30 | 387
[75 empty] | 2025-10-01 | 388
[75 empty] | 2025-10-02 | 389
[75 empty] | 2025-10-03 | 390
2025-10-04
2025-10-05
[75 empty] | 2025-10-06 | 391
[75 empty] | 2025-10-07 | 392
[75 empty] | 2025-10-08 | 393
[75 empty] | 2025-10-09 | 394
[75 empty] | 2025-10-10 | 395
2025-10-11
2025-10-12
[75 empty] | 2025-10-13 | 396
[75 empty] | 2025-10-14 | 397
[75 empty] | 2025-10-15 | 398
[75 empty] | 2025-10-16 | 399
[75 empty] | 2025-10-17 | 400
2025-10-18
2025-10-19
[75 empty] | 2025-10-20 | 401
[75 empty] | 2025-10-21 | 402
[75 empty] | 2025-10-22 | 403
[75 empty] | 2025-10-23 | 404
[75 empty] | 2025-10-24 | 405
2025-10-25
2025-10-26
[75 empty] | 2025-10-27 | 406
[75 empty] | 2025-10-28 | 407
[75 empty] | 2025-10-29 | 408
[75 empty] | 2025-10-30 | 409
[75 empty] | 2025-10-31 | 410
2025-11-01
2025-11-02
[75 empty] | 2025-11-03 | 411
[75 empty] | 2025-11-04 | 412
[75 empty] | 2025-11-05 | 413
[75 empty] | 2025-11-06 | 414
[75 empty] | 2025-11-07 | 415
2025-11-08
2025-11-09
[75 empty] | 2025-11-10 | 416
[75 empty] | 2025-11-11 | 417
[75 empty] | 2025-11-12 | 418
[75 empty] | 2025-11-13 | 419
[75 empty] | 2025-11-14 | 420
2025-11-15
2025-11-16
[75 empty] | 2025-11-17 | 421
[75 empty] | 2025-11-18 | 422
[75 empty] | 2025-11-19 | 423
[75 empty] | 2025-11-20 | 424
[75 empty] | 2025-11-21 | 425
2025-11-22
2025-11-23
[75 empty] | 2025-11-24 | 426
[75 empty] | 2025-11-25 | 427
[75 empty] | 2025-11-26 | 428
[75 empty] | 2025-11-27 | 429
[75 empty] | 2025-11-28 | 430
2025-11-29
2025-11-30
[75 empty] | 2025-12-01 | 431
[75 empty] | 2025-12-02 | 432
[75 empty] | 2025-12-03 | 433
[75 empty] | 2025-12-04 | 434
[75 empty] | 2025-12-05 | 435
2025-12-06
2025-12-07
[75 empty] | 2025-12-08 | 436
[75 empty] | 2025-12-09 | 437
[75 empty] | 2025-12-10 | 438
[75 empty] | 2025-12-11 | 439
[75 empty] | 2025-12-12 | 440
2025-12-13
2025-12-14
[75 empty] | 2025-12-15 | 441
[75 empty] | 2025-12-16 | 442
[75 empty] | 2025-12-17 | 443
[75 empty] | 2025-12-18 | 444
[75 empty] | 2025-12-19 | 445
2025-12-20
2025-12-21
[75 empty] | 2025-12-22 | 446
[75 empty] | 2025-12-23 | 447
[75 empty] | 2025-12-24 | 448
[75 empty] | 2025-12-25 | 449
[75 empty] | 2025-12-26 | 450
2025-12-27
2025-12-28
[75 empty] | 2025-12-29 | 451
[75 empty] | 2025-12-30 | 452
[75 empty] | 2025-12-31 | 453
[75 empty] | 2026-01-01 | 454
[75 empty] | 2026-01-02 | 455
2026-01-03
2026-01-04
[75 empty] | 2026-01-05 | 456
[75 empty] | 2026-01-06 | 457
[75 empty] | 2026-01-07 | 458
[75 empty] | 2026-01-08 | 459
[75 empty] | 2026-01-09 | 460
2026-01-10
2026-01-11
[75 empty] | 2026-01-12 | 461
[75 empty] | 2026-01-13 | 462
[75 empty] | 2026-01-14 | 463
[75 empty] | 2026-01-15 | 464
[75 empty] | 2026-01-16 | 465
2026-01-17
2026-01-18
[75 empty] | 2026-01-19 | 466
[75 empty] | 2026-01-20 | 467
[75 empty] | 2026-01-21 | 468
[75 empty] | 2026-01-22 | 469
[75 empty] | 2026-01-23 | 470
2026-01-24
2026-01-25
[75 empty] | 2026-01-26 | 471
[75 empty] | 2026-01-27 | 472
[75 empty] | 2026-01-28 | 473
[75 empty] | 2026-01-29 | 474
[75 empty] | 2026-01-30 | 475
2026-01-31
2026-02-01
[75 empty] | 2026-02-02 | 476
[75 empty] | 2026-02-03 | 477
[75 empty] | 2026-02-04 | 478
[75 empty] | 2026-02-05 | 479
[75 empty] | 2026-02-06 | 480
2026-02-07
2026-02-08
[75 empty] | 2026-02-09 | 481
[75 empty] | 2026-02-10 | 482
[75 empty] | 2026-02-11 | 483
[75 empty] | 2026-02-12 | 484
[75 empty] | 2026-02-13 | 485
2026-02-14
2026-02-15
[75 empty] | 2026-02-16 | 486
[75 empty] | 2026-02-17 | 487
[75 empty] | 2026-02-18 | 488
[75 empty] | 2026-02-19 | 489
[75 empty] | 2026-02-20 | 490
2026-02-21
2026-02-22
[75 empty] | 2026-02-23 | 491
[75 empty] | 2026-02-24 | 492
[75 empty] | 2026-02-25 | 493
[75 empty] | 2026-02-26 | 494
[75 empty] | 2026-02-27 | 495
2026-02-28
2026-03-01
[75 empty] | 2026-03-02 | 496
[75 empty] | 2026-03-03 | 497
[75 empty] | 2026-03-04 | 498
[75 empty] | 2026-03-05 | 499
[75 empty] | 2026-03-06 | 500
2026-03-07
2026-03-08
[75 empty] | 2026-03-09 | 501
[75 empty] | 2026-03-10 | 502
[75 empty] | 2026-03-11 | 503
[75 empty] | 2026-03-12 | 504
[75 empty] | 2026-03-13 | 505
2026-03-14
2026-03-15
[75 empty] | 2026-03-16 | 506
[75 empty] | 2026-03-17 | 507
[75 empty] | 2026-03-18 | 508
[75 empty] | 2026-03-19 | 509
[75 empty] | 2026-03-20 | 510
2026-03-21
2026-03-22
[75 empty] | 2026-03-23 | 511
[75 empty] | 2026-03-24 | 512
[75 empty] | 2026-03-25 | 513
[75 empty] | 2026-03-26 | 514
[75 empty] | 2026-03-27 | 515
2026-03-28
2026-03-29
[75 empty] | 2026-03-30 | 516
[75 empty] | 2026-03-31 | 517
[75 empty] | 2026-04-01 | 518

## ToU
TERMS OF USE
END USER LICENSE AGREEMENT
This End-User License Agreement is a legal agreement between you and someka.net that covers all Microsoft Excel templates, spreadsheets or software built by someka.net.
By downloading, copying, accessing or otherwise using any of these templates, you agree to abide by the following terms:
* You may NOT sell, resell, license, rent, lease, lend or otherwise transfer for value without written permission of someka.net * Unless you've purchased the proper license rights, you may NOT remove or alter any someka.net logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within the template. * You may NOT distribute, publish to an online gallery, host on a website, or place on any server in a way that makes it available to the general public.
RESERVATION OF RIGHTS
All title and copyrights in and to the Template, and any copies of the Template, are owned by someka.net. All rights not expressly granted are reserved by someka.net. Use of any Template for any purpose other than expressly permitted in this EULA is prohibited, and may result in severe civil and criminal penalties.
CONTACT
For more information and specific permissions for your case, please contact us at: contact@someka.net
Back to
Menu